## Sheet1
Work Breakdown Study (WBS)
Total Hours Used:
Phases: |  | Task |  |  | Estimate Hrs Spent | Hourly Rate | Invoiced Amount
Phase 1 | Branstorming/Planning |  |  |  | 14.5 | 25 | 362.5
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8
| 1.1 | Proposal |  |  | 1 | 25 | 25
| 1.2 | Sketch of Design |  |  | 6 | 25 | 150
| 1.2.1 | Font |  |  | 1.5 | 25 | 37.5
| 1.2.2 | Colour |  |  | 1.5 | 25 | 37.5
| 1.2.3 | Layout |  |  | 2 | 25 | 50
| 1.2.4 | Navigation |  |  | 1 | 25 | 25
| 1.4 | Social Media |  |  | 0 | 25 | 0
| 1.5 | Wireframes and Mockups |  |  | 2 | 25 | 50
| 1.5.1 | Wireframes |  |  | 1 | 25 | 25
| 1.5.2 | Mockups |  |  | 1 | 25 | 25
| 1.6 | Images |  |  | 5 | 25 | 125
| 1.6.1 | Acquiring Images |  |  | 3 | 25 | 75
| 1.6.2 | Photoshop Images |  |  | 2 | 25 | 50
| 1.7 | Make Decisions |  |  | 0.5 | 25 | 12.5
MILESTONE CHECKPOINT 1
Phase 2 | HTML/CSS/JavaScript/Jquery/php |  | 2019-10-31 | 2019-11-28 | 41.5 | 25 | 1037.5
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8
| 2.1 | Sketch of Design |  |  | 0 | 25 | 0
| 2.1.1 | Font |  |  | 0 | 25 | 0
| 2.2.2 | Colour |  |  | 0 | 25 | 0
| 2.2.3 | Layout |  |  | 0 | 25 | 0
| 2.2.4 | Navigation |  |  | 0 | 25 | 0
| 2.2 | Social Media |  |  | 0 | 25 | 0
| 2.3 | Wireframes and Mockups |  |  | 0 | 25 | 0
| 2.3.1 | Wireframes |  |  | 0 | 25 | 0
| 2.3.2 | Mockups |  |  | 0 | 25 | 0
| 2.4 | Images |  |  | 0.5 | 25 | 12.5
| 2.4.1 | Acquiring Images |  |  | 0 | 25 | 0
| 2.4.2 | Photoshop Images |  |  | 0.5 | 25 | 12.5
| 2.5 | Implement technical framework (html) |  |  | 10 | 25 | 250
| 2.5.1 | Build or acquire back end |  |  | 4 | 25 | 100
| 2.5.2 | Build or acquire front end |  |  | 4 | 25 | 100
| 2.5.3 | Integrate back and front end |  |  | 2 | 25 | 50
| 2.6 | Implement technical framework (CSS) |  |  | 14 | 25 | 350
| 2.6.1 | Build or acquire back end |  |  | 6 | 25 | 150
| 2.6.2 | Build or acquire front end |  |  | 6 | 25 | 150
| 2.6.3 | Integrate back and front end |  |  | 2 | 25 | 50
| 2.7 | Implement technical framework (Javascript/JQuery) |  |  | 3 | 25 | 75
| 2.7.1 | Build or acquire back end |  |  | 1 | 25 | 25
| 2.7.2 | Build or acquire front end |  |  | 1 | 25 | 25
| 2.7.3 | Integrate back and front end |  |  | 1 | 25 | 25
| 2.8 | Implement technical framework (Contact form) |  |  | 2 | 25 | 50
| 2.8.1 | Build or acquire back end |  |  | 0 | 25 | 0
| 2.8.2 | Build or acquire front end |  |  | 1 | 25 | 25
| 2.8.3 | Integrate back and front end |  |  | 1 | 25 | 25
| 2.9 | Implement technical framework (php) |  |  | 5 | 25 | 125
| 2.9.1 | Build or acquire back end |  |  | 3 | 25 | 75
| 2.9.2 | Build or acquire front end |  |  | 1 | 25 | 25
| 2.9.3 | Integrate back and front end |  |  | 1 | 25 | 25
| 2.10. | Evaluation |  |  | 4 | 25 | 100
| 2.10.1 | W3 html/CSS Validation |  |  | 1 | 25 | 25
| 2.10.2 | Accessibility |  |  | 1 | 25 | 25
| 2.10.3 | Mobile Responsiveness |  |  | 2 | 25 | 50
| 2.11 | Quality Assurance |  |  | 1 | 25 | 25
| 2.12 | User Testing |  |  | 2 | 25 | 50
MILESTONE CHECKPOINT 2
Phase 3 | Roll Out Site/Site Launching Preparation |  | 2019-11-29 | 2019-12-13 | 17.5 | 25 | 437.5
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8
| 3.1 | Sketch of Design |  |  | 0 | 25 | 0
| 3.1.1 | Font |  |  | 0 | 25 | 0
| 3.1.2 | Colour |  |  | 0 | 25 | 0
| 3.1.3 | Layout |  |  | 0 | 25 | 0
| 3.1.4 | Navigation |  |  | 0 | 25 | 0
| 3.2 | Social Media |  |  | 0 | 25 | 0
| 3.3 | Wireframes and Mockups |  |  | 0 | 25 | 0
| 3.3.1 | Wireframes |  |  | 0 | 25 | 0
| 3.3.2 | Mockups |  |  | 0 | 25 | 0
| 3.4 | Images |  |  | 0 | 25 | 0
| 3.4.1 | Acquiring Images |  |  | 0 | 25 | 0
| 3.4.2 | Photoshop Images |  |  | 0 | 25 | 0
| 3.5 | Implement technical framework (html) |  |  | 2 | 25 | 50
| 3.5.1 | Build or acquire back end |  |  | 0.5 | 25 | 12.5
| 3.5.2 | Build or acquire front end |  |  | 1 | 25 | 25
| 3.5.3 | Integrate back and front end |  |  | 0.5 | 25 | 12.5
| 3.6 | Implement technical framework (CSS) |  |  | 4 | 25 | 100
| 3.6.1 | Build or acquire back end |  |  | 1 | 25 | 25
| 3.6.2 | Build or acquire front end |  |  | 2 | 25 | 50
| 3.6.3 | Integrate back and front end |  |  | 1 | 25 | 25
| 3.7 | Implement technical framework (Javascript/JQuery) |  |  | 1.5 | 25 | 37.5
| 3.7.1 | Build or acquire back end |  |  | 0.5 | 25 | 12.5
| 3.7.2 | Build or acquire front end |  |  | 0.5 | 25 | 12.5
| 3.7.3 | Integrate back and front end |  |  | 0.5 | 25 | 12.5
| 3.8 | Implement technical framework (Contact form) |  |  | 0 | 25 | 0
| 3.8.1 | Build or acquire back end |  |  | 0 | 25 | 0
| 3.8.2 | Build or acquire front end |  |  | 0 | 25 | 0
| 3.8.3 | Integrate back and front end |  |  | 0 | 25 | 0
| 3.9 | Implement technical framework (php) |  |  | 2.5 | 25 | 62.5
| 3.9.1 | Build or acquire back end |  |  | 1 | 25 | 25
| 3.9.2 | Build or acquire front end |  |  | 0.5 | 25 | 12.5
| 3.9.3 | Integrate back and front end |  |  | 1 | 25 | 25
| 3.10. | Evaluation |  |  | 1.5 | 25 | 37.5
| 3.10.1 | W3 html/CSS Validation |  |  | 0.5 | 25 | 12.5
| 3.10.2 | Accessibility |  |  | 0 | 25 | 0
| 3.10.3 | Mobile Responsiveness |  |  | 1 | 25 | 25
| 3.11 | Quality Assurance |  |  | 1 | 25 | 25
| 3.12 | User Testing |  |  | 2 | 25 | 50
| 3.13 | Web Domain |  |  | 1 | 25 | 25
| 3.14 | Web Hosting |  |  | 2 | 25 | 50
|  | Estimated ToT: | 87567 |  | 73.5
|  | Hourly Rate: |  | 87609 |  | 25
|  | Total Invoiced Amount: |  |  |  |  | 1837.5
TOTAL BUDGET INCLUDING RISK AND OVERHEAD:
| NET COST (Based on ToT): |  |  |  |  | 1837.5
| RISK: |  |  |  | 15% | 275.625
| OVERHEAD: |  |  |  | 25% | 459.375
| TOTAL BUDGET: |  |  |  |  | 2572.5